## PRODUCT BACKLOG
PRODUCT BACKLOG EXAMPLE (Game of the Goose)
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Make menu | Coding, Visualize | M | done
1 | Show the rules of the game when needed by user | Coding, Visualize | M | doing
2 | Select the number of players | Coding, Visualize | M | done
3 | Visualize the game board | Coding, Visualize | M | done
4 | Visualize the game cards | Coding, Visualize | M |  | doing
5 | Code movements on the game board | Coding, Visualize | M |  | doing
6 | Implement attack values | Coding | M |  | doing
7 | Implement defence values | Coding | M |  | doing
8 | Implement the army units | Coding | M |  | doing
9 | Implement the prices | Coding | M |  | doing
10 | Implement total bank value per player | Coding | M |  | doing
11 | Implement boats | Coding, Visualize | M
12 | Display which player is playing the current turn | Coding, Visualize | M
13 | Give every tile a position(coordinate) | Coding, Visualize | M |  | doing
14 | Show win screen if current player achieved a win condition | Coding, Visualize | M | doing
15 | Make the ERD | Visualize | M | done
16 | Implement buttons in the rules | Coding, Visualize | S |  | doing
17 | Implement pause menu | Coding, Visualize | C
18 | Implement Audio | Coding, Visualize | C
19 | Implement animations | Coding, Visualize | C
20 | Implement settings menu | Coding, Visualize | C
21 | Implement computer as opponent: AI | Coding, Visualize | C
22 | Implement savegames(save & load) | Coding, Visualize | S
23 | Implement web game | Coding, Visualize | C
24 | Implement multiplayer in LAN or online | Coding, Visualize | C
| Menu with "start game" and "exit" buttons | Menu | M
| Show the rules of the game when needed by user | Menu or Turn | M
| Screen to select the number of players | Init | M
| Display game board | Init | M
| Place all pawns on first tile | Init | M
| Display "exit" button | Init and Turn | M
| Display which player is playing the current turn | Turn | M
| Current player can roll the dice and see the result | Turn | M
| Move the pawn of the player forward according to dice result | Turn | M
| Execute special actions (for example, go back to tile 1) according to the tile on which the player arrives | Turn | M
| Change current player after the end of the turn | Turn | M
| Show win screen if current player arrives to end tile and display name of winner | End | M
| "Go back to menu" button is displayed in the win screen | End | S
| Current player can pause and resume the game | Turn | S
| Produce sound for throw of a dice / moving pawn / win screen / special actions | Turn | C
| Display dice throw / moving pawn with an animation | Turn | C
| Menu extended with "settings" button (for example, containing screen resolution, audio volume, …) | Menu | C
| Possibility to select also computer players | Init | C
| Computer player is able to play the game | Turn | C
| Add some humour to the computer player | Turn | W
| Save current state of the game on a file | Turn | C
| Load a previously saved game state | Menu | C
| Make game playable online | Browser | C
| Make game playable by users sitting at different PCs (LAN multiplayer) | Menu and Turn | C

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
0 | As a player I want to start or quit the game from the menu, so that I can play it or stop playing | M | 5 | - Find a proper texture for the start and the quit button. - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on start button, run game | - Buttons displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on game start - Clicks on the button area make the screen change (to init phase)
15 | As a product owner I want an ERD, so that I can see the entity sets and the attributes easily | M | 8 | - make an ERD | - The ERD must have the right attributes - The ERD must have the right entities.
1 | As a player I want to see the rules when I need them, so that I understand how to play the game | M | 2 | - Find the rules - When a specific button is pressed, show the rules - choose a font | - The rules are correct - The rules are easy accessible - The rules are readable, not complete is not important.
2 | As a player I want to select the amount of players, so that I can play with the selected amount of players | M | 13 | - Make the option to choose how many players will be playing | - A player can select the amount of players at the beginning of every game - The amount of players must be between 2 and 4 players
14 | As a Player I want a winning screen so that I can see when the game is ended | M | 2 | - Make a winning screen | - The screen must be showed when a certain condition is met. - The playername of the winner must be shown
3 | As a Player I want a fancy gameboard on the screen, so that the game more attrictive is to play | M | 13 | - Make textures for the climates, goldmine island and water - add values to the Tiles (for Water, Ice etc. - Code tiles and connect the textures with the tiles - Generate Tiles in the map to connect attributes to | - The screen must be showed when a certain condition is met. - The screen must be made out of Tiles
EXAMPLE
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a player I want to start the game from the menu, so that I can play it. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on start button, init game | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on game start - Clicks on the button area make the screen change (to init phase)
1 | As a player I want to quit the program from the menu, so that I can stop playing. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on exit button, quit program | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on quit program - Clicks on the button area make the program quit

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
13 | As a player I want every tile to have a position so that I can see the position and place pawns on it. | M | 8 | - Extract Position from Tile -Display Position on PyGame -Make it possible to move pawns on tiles from position. | - positions must be correct
4 | As a player I want to see the cards so that I can see what card I got | M | 8 | - Cards must be shown when a condition is met. | -The right values must be added by the cards.
5 | As a Player I want to move my pawns so that I can play the game. | M | 13 | - Get position from tile - Get max range/movement fromt attribute - Move the pawn | - Movements must be according to the rule and right.
6 | As a player I want attack values linked to my units so that my units can win a fight. | M | 3 | - Link attack values to units | - The right values, according to the rules, must be added by the units.
7 | As a player I want defence values linked to my units so that my units can win a fight. | M | 3 | - Link defence values to units | - The right values, according to the rules, must be added by the units.
8 | As a player I want units so that I can play the game using units. | M | 13 | - Make for ecery unit textures - Make the units appear on the map - assign units to a player | - The right values, according to the rules, must be added by the units.
9 | As a user I want prices/currency so that I can use my (in game) money. | M | 5 | - Add currency - add prices to units - Add price diffirences to biomes | - Must be according to the rules.
10 | As player I want a bank value so that I can buy units | M | 3 | - add bank values to players | - Each player have a bank value
16 | As player I want buttons in the rules so that the rules are more read | M | 13 | - implement buttons | - The rules are correct